Guide2. APT Project Development

Capstone Subject

1. Summary of APT Project Progress

Below, you will find different fields that you must fill in with the requested information.

| APT Project Progress Summary | During the development of the "HouseCountSimulator" project, we have advanced from the design phase to the technical implementation of the simulator, meeting key specific objectives such as the structuring of the backend through containerization with Docker, the Django framework and the deployment of a REST API, as well as the construction of the interactive 3D viewer that integrates more than 140 models and allows authenticated users to save, manage and dynamically value their custom designs. In terms of methodology, although the general objectives of the project remain intact, we applied operational adjustments aimed at continuous improvement in our Scrum and version control workflow: we standardized the naming of the commits to guarantee traceability with the User Stories, we excluded the database from the central repository to avoid integration conflicts and make the extension of the Sprints in our Burndown Chart control more flexible to adapt to the real duration in working days demanded by the technical complexity of each phase. |
| --- | --- |
| Objectives | Develop an interactive web application that allows users to plan and quote the construction materials for a home, adjusting to the available options based on a defined maximum budget. For the section of more technical objectives: - Interactive 3D Simulation: Provide an interactive modular tool for designing homes step by step. - Rapid Build Catalog: Have pre-designed and optimized models to speed up decision-making. - Personalized advice: Offer a direct contact channel to manage tailor-made requests. - System support and reporting: Generate automatic reports that document and safeguard design and budget data. |
| Methodology | To address financial misinformation and the lack of technical advice in self-construction, the solution will be developed and implemented through the "HouseCountSimulator" web platform. The project will be managed under the agile Scrum methodology, structured in work phases over 18 weeks. This approach allows for continuous validation of customer and user requirements, ensuring continuous deliveries and minimizing scope risks. Regarding the organization of group work, the team will distribute its roles and responsibilities in the following areas of performance: Product Owner: Benjamin Isaac Casellas Madrid. Master Scrum: Benjamín Tomás Núñez Arancibia. Developers: Emilio Castro González. Tester Q&A : Lucas Ignacio Padilla Aliaga. |
| Evidence of progress | As a method of evidencing the work carried out, two fundamental tools have been provided. First, to maintain adequate control and organization of the activities assigned to each team member, a Kanban board implemented on the Trello platform is used. This tool allows flexible management aligned with the Scrum methodology adopted by the group, in addition to providing transparency regarding pending, in progress and completed tasks, as well as the priorities defined for the development of the project. On the other hand, all the documentation and progress related to the development of the solution are stored in a GitHub repository with the same name as the project. To avoid conflicts between the members and facilitate collaborative work, each member develops their contributions in an independent branch. Subsequently, the validated changes are integrated into the main branch, allowing them to centralize and maintain a stable version of the project. links to evidence presented in the "HouseCountSimulator" project: TRELLO table link: - https://trello.com/b/C5HWPLek/kanban-scrum-housecount GitHub Project Repository: - https://github.com/Benjaminunez/HomeCount_Simulator.git |

2. Monitoring of the Work Plan

Carefully examine your work plan, focusing especially on the progress status and adjustments column.

| "HouseCountSimulator" workplan |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Competence or units of competences | Activities | Resources | Duration of the activity | Responsible | Observations | Progress status | Settings |
| Develop a software solution | Scrum Base Documents: Team Roles and Self-Assessments by Member | Trello, Google Drive, Discord, AVA | 03-09 to 06-09 | The whole team Editor: Benjamín Casellas | Facilitated: deliverables and clear deadlines from retrospective #1. Difficulty: the official communication channel was not defined. | Completed | It was agreed to define an official channel of communication and a space for consensus in the meetings. |
| Develop a software solution | Scrum Templates: Product Backlog, Sprint Backlog, Burndown Chart and Sprint 1 validation | Trello, Google Drive | 11-09 to 13-09 | The entire team, form Responsible: Benjamín Núñez | A misunderstanding about the Sprint closing documentation was resolved in the same session (retro #4). | Completed | Flexible duration of the Sprints in the Burndown according to the actual working days. |
| Develop a software solution | Scrum ceremonies: sprint starts, progress shows and retrospectives | Discord, Trello, Retrospective Form | 03-09 to 13-10 (continued) | Benjamín Núñez and the whole team | Almost complete attendance. From 01-10 a member began his professional practice and his availability decreased. | Completed | Simultaneous work sessions on Discord and periodic group reviews (retro #2). |
| Offer IT solution proposals | Economic WBS of the project and reinforcement of documentation | Trello, Google Drive | Until 05-10 (80% progress on that date) | The whole team Manager: Lucas Padilla | Goal: 50% delivery set for 13-10. It was agreed to update the documents as the software grows. | Completed | None |
| Building the architectural model of a solution | 4+1 Model Views in UML: Logic, Physics, Scenarios, Deployment, and Processes | Support material in Trello, Google Drive | 21-09 to 23-09 | The whole team, Manager: Benjamín Núñez | Architectural design began in Sprint 2 and closed in Sprint 3. | Completed | None |
| - Offer IT solution proposals - Develop a software solution | Initial functional prototype with 3D simulation of basic housing | GitHub, Discord | 04-09 to 07-09 | Benjamín Casellas | It was uploaded to the repository for the 08-09 exhibition, in retro #4 the 3D advance was highlighted. | Completed | It was agreed to expand it with new pieces and structures. |
| Develop a software solution | Docker container and migration of the prototype to the Django framework | Docker Desktop, Django, GitHub | Sprint 3 (until 21-09) | The whole team Editor: Emilio Castro | Facilitated: standardized environment. Difficulty: Docker Desktop and virtualization requirements on a computer (retro #7). | Completed | Database excluded from the repository to avoid integration conflicts. |
| - Build data models - Schedule database queries or routines | Backend: REST API and database, validated with Postman (GET, POST, PUT) | Django, SQLite, Postman | Sprint 3 (until 23-09) | The whole team Editor: Benjamín Núñez | Seamless communication between the database and REST services. | Completed | None |
| - Develop a software solution - Schedule database queries or routines | 3D viewer, loading of models (more than 140) and registration of models in the database | Modelos .glb, Django, SQLite, GitHub | 23-09 to 05-10 | Lucas Padilla | Difficulties: .glb did not retain their original size and models larger than 5 MB load slowly. | Completed | Heavy model optimization and responsive 3D view agreed as an enhancement |
| - Develop a software solution - Resolve systemic vulnerabilities | Registration and authentication of users, roles (Administrator and User) and management of saved designs | Django, SQLite | 23-09 to 05-10 | The whole team Editor: Benjamín Casellas | Planned in retro #6, with progress in #7 and differentiated roles in #8. | Completed | None |
| Develop a software solution | Calculation of square meters per 3D model | Visor 3D, JavaScript, Trello | From 01-10 (no deadline set) | Emilio Castro | Technical difficulty with three-dimensional objects. | In progress | Its final integration into the ongoing sprint is prioritized. |
| Develop a software solution | Home view and visual improvements of external screens to the 3D canvas | Trello, GitHub | From 23-09 (interface redesign) | The whole team Editor: Emilio Castro | Interface redesign well received, lack of visual coherence in secondary views. | Completed | Improve the design of the screens outside the canvas (retro #8). |
| Transversal: all the competences of the project | Group Guide 2.1 and Personal Self-Assessment 2.1 (Phase 2) | Trello, Google Drive, AVA | Wins 18-10 | The whole team (guide), each member (self-evaluation) | Near term. Facilitated: tracking by cards in Trello. | Completed | None |

3. Adjustments from monitoring

Dig deeper into the observations in your work plan. Analyze the planned activities and point out what aspects facilitated or hindered the execution of the plan. Discuss how you addressed and/or will address the obstacles. Finally, point out the adjustments you made to the work plan based on this analysis.

Factors that have facilitated and/or hindered the development of my work plan: - Communication and clear roles: From the first retrospectives, the team was able to clearly establish the responsibilities, deliverables, and deadlines of each member. In addition, the constant use of Discord and the improvement in verbal communication strengthened coordination, trust, and collaborative work. - Management tools: The implementation of Trello as the main tracking tool, together with the use of Google Drive for the storage and management of documents, made it possible to maintain a better organization of tasks, facilitating access to information and controlling the progress of the project. - Standardized technical foundation: Adopting a Docker container and migrating to Django provided a common working foundation for the entire team. This facilitated the development and integration of functionalities such as REST API, role-based authentication, and 3D model management. - Work pace: The periodic review and retrospective instances contributed to maintaining constant progress. As a result, a high level of progress was achieved in the documentation associated with Scrum, Architecture and Economic WBS, evidencing adequate planning and execution of the activities. Difficulties and actions taken or to be taken - Teamwork and personal time: During the early stages of the project, a perception of individualized work and a lower availability of time during weekends were identified. To address this situation, simultaneous work sessions were promoted through Discord, periodic group reviews, and more active communication through voice calls and videoconferences. - Calendar and academic load: The progress of the project was temporarily affected by periods of high academic load, the celebrations of National Holidays and the beginning of the professional practice of one of the members. It was also necessary to dedicate additional time to the accompaniment and orientation of some members regarding their assigned tasks. As a mitigation measure, the planning of the sprints was adjusted to the effective working days and the explicit assignment of responsibilities through Trello was reinforced. - Technical environment: Difficulties associated with the configuration of Docker Desktop and virtualization requirements on some computers were encountered. In addition, problems related to the scaling of the 3D models in. glb format, and the processing times of large files were detected. To solve these situations, we worked collaboratively on the configuration of the development environments and considered the optimization of the heavier models. - Complexity of key functionalities: Some functionalities were more complex to implement than initially estimated, particularly the calculation of surfaces in 3D models and the integration of an open-source materials API. This situation required greater efforts of research, testing and evaluation of technical alternatives to ensure a solution appropriate to the context of the project.

Adjusted or removed activities: The overall objectives of the project are maintained, so adjustments were concentrated on the way of working and technical decisions. Activities were not removed from the scope. - Version control: To strengthen traceability and monitoring of the work done, the team standardized the naming of the commits, linked directly to the corresponding User Stories. Likewise, it was decided to exclude the database from the central repository to avoid conflicts during the integration and synchronization processes of the code. - Scrum Planning: The planning of the Sprints was flexibly adapted to the actual availability of the members and the working days of each period. As part of this improvement, adjustments were made to the Burndown Chart and some documentation deadlines were promptly extended when circumstances required it, thus guaranteeing the fulfillment of the established objectives. - Work organization: To improve the management and coordination of activities, Trello was reorganized into two different spaces: one for monitoring meetings and the other focused on task management. Additionally, an official communication channel was defined, and simultaneous collaborative work sessions were incorporated through Discord, strengthening coordination and accompaniment among members. - Technical decisions: As the project progressed, technical decisions were made aimed at improving scalability and product quality. These included migrating the initial prototype to a Django and Docker-based architecture, transitioning from three-dimensional models with a simplified style to more realistic models, and evaluating replacing SQLite with a more robust and scalable database management system. - Refocusing effort: Based on the retrospectives carried out during the project, the team agreed to allocate a greater proportion of the available time to the development and implementation of software functionalities. This measure made it possible to prioritize the most relevant technical advances and focus efforts on the objectives necessary for the final delivery of the project.

Activities you haven't started or are delayed: As of 18-10 these activities are still open or behind schedule: - Square Meter Calculation for 3D Models (in Progress): This functionality is still in development due to the technical complexity associated with calculating areas on three-dimensional objects. To address this challenge, the team agreed to prioritize this task within the current sprint and work on it through collaborative sessions on Discord, to accelerate the research and validation of potential solutions. - Catalog of materials with open-source API: So far, no API has been identified that adequately meets the requirements of the project and allows for easy integration. As a strategy, the team will continue to evaluate available alternatives and, if a viable option is not found, a proprietary catalog stored in the database will be implemented to ensure the operation of the quotation system. - Visual improvements to the home view and the screens outside the 3D canvas (in progress): While the main efforts have been concentrated on the core functionalities of the system, improvements related to the main view and the external screens to the 3D modeling environment are still under development. To this end, it has been planned to allocate part of the time available in the next sprints to the refinement of the interface, seeking a coherent and uniform visual experience throughout the application. - Group guide and self-evaluations 2.1: Some academic activities associated with the project are still in the process of preparation and review. To meet the established deadlines, the team has planned to finalize the pending documents and carry out the corresponding revisions before the delivery date. - Record of the 08-10 retrospective: Although the retrospective form has already been created, the main successes, errors and recommendations identified by the team still need to be recorded. It was agreed to complete this information during the next retrospective session to keep the documentation updated and properly record the lessons learned during the development of the project.

4. Annexes

- Documento_Consolidado_Reuniones_Retrospectivas_HomeCount_Simulator.pdf - https://trello.com/b/C5HWPLek/kanban-scrum-housecount